## budget after 10-2014
eumetsat_share = 50% |  | (development tasks and their validation)
eumetsat_share = 75% |  | operations and QA |  |  |  |  | CDOP-2 budget, 12/2014
changes related to entity report 10/2014
wp_start= 03/2012
wp_end= 02/2017
WP type | WP# | WP title | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | Tot mm | mm rate | price | EUM price | EUM share | [5 empty] | O3 | NO2 | BrO | SO2 | OCLO | HCHO | CHOCHO | S4/S5 | HNO3 | reprocessing
| 1001 | Scientific & techn. coordination | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0.5 | 6.96 | 3.48 | 2.61 | 0.75
[17 empty] | dev+valid | 2014 | 0 | 7 | 1 | 4.5 | 1 | 4 | 1 | 3 | 0 | 4 | ...from 2013
Development | 1101 | GOME2 Total O3 | 3 | 2 | 0 | 0 | 0 | 0 | 5 | 6.96 | 34.8 | 17.4 | 0.5 |  |  |  |  | 2015 | 0 | 5 | 6 | 4.5 | 4 | 1.5 | 5.5 | 3.25 | 3 | 0
| 1201 | GOME2 Total NO2 | 0.7 | 1 | 1 | 2 | 0.7 | 0 | 5.4 | 6.96 | 37.584 | 18.792 | 0.5 |  |  |  |  | 2016 | 0 | 3.4 | 3.1 | 4.7 | 2.7 | 2.2 | 5.2 | 2 | 3 | 7
| 1202 | GOME2 Tropospheric NO2 | 0.7 | 1 | 1 | 2 | 0.7 | 0 | 5.4 | 6.96 | 37.584 | 18.792 | 0.5 |  |  |  |  | 2017 | 0 | 0.25 | 0.25 | 0.5 | 0.25 | 0.25 | 0.25 | 0 | 0.25 | 0
| 1301 | GOME2 Total BrO | 0.7 | 1 | 0 | 1 | 0.7 | 0 | 3.4 | 6.96 | 23.664 | 11.832 | 0.5
| 1302 | GOME2 SO2 | 0.7 | 1 | 2 | 1 | 0.7 | 0 | 5.4 | 6.96 | 37.584 | 18.792 | 0.5 |  |  |  |  | tot | 0 | 15.65 | 10.35 | 14.2 | 7.95 | 7.95 | 11.95 | 8.25 | 6.25 | 11
| 1303 | GOME2 OClO | 0.3 | 1.7 | 1 | 1 | 0.7 | 0 | 4.7 | 6.96 | 32.712 | 16.356 | 0.5
| 1304 | GOME2 HCHO | 0.7 | 1 | 2 | 1 | 0.7 | 0 | 5.4 | 6.96 | 37.584 | 18.792 | 0.5
| 1306 | GOME2 CHOCHO | 3 | 1 | 1 | 2 | 0.7 | 0 | 7.7 | 6.96 | 53.592 | 26.796 | 0.5
| 1311 | GOME2 Tropospheric BrO | 3 | 2 | 0 | 2 | 0.4 | 0 | 7.4 | 6.96 | 51.504 | 25.752 | 0.5 |  |  |  | dev | 2014 | 0 | 2 | 0 | 2 | 1 | 2 | 1 | 0 | 0 | 0
[18 empty] | 2015 | 0 | 4 | 3 | 1 | 1 | 1 | 2 | 0 | 0 | 0
| 1610 | S4/ S5 (P) | 0 | 2 | 3 | 3.25 | 2 | 0 | 10.25 | 6.96 | 71.34 | 35.67 | 0.5 |  |  |  |  | 2016 | 0 | 1.4 | 1.1 | 0.7 | 0.7 | 0.7 | 0.7 | 0 | 0 | 0
[18 empty] | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Validation | 4201 | GOME2 NO2 validation & QA | 1 | 1 | 1 | 1 | 1 | 0.25 | 5.25 | 6.96 | 36.54 | 27.405 | 0.75 | QA
|  |  | 0 | 1 | 4 | 0 | 1 | 0 | 6 | 6.96 | 41.76 | 20.88 | 0.5 | valid |  |  |  | tot | 0 | 7.4 | 4.1 | 3.7 | 2.7 | 3.7 | 3.7 | 0 | 0 | 0
| 4301 | GOME2 BrO validation & QA | 0.5 | 1 | 1 | 1 | 1 | 0.25 | 4.75 | 6.96 | 33.06 | 24.795 | 0.75 | QA
|  |  | 0.5 | 1 | 0 | 2 | 1 | 0 | 4.5 | 6.96 | 31.32 | 15.66 | 0.5 | [13 empty] | tot per year:
| 4302 | SO2 validation & QA | 0.5 | 0.5 | 1 | 1 | 1 | 0.5 | 4.5 | 6.96 | 31.32 | 23.49 | 0.75 | QA |  |  | QA | 2014 | 0 | 1 | 1 | 1 | 0 | 0.5 | 0 |  | 3.5 | 2014
|  |  | 0 | 3 | 1.5 | 2.5 | 3 | 0 | 10 | 6.96 | 69.6 | 34.8 | 0.5 |  |  |  |  | 2015 | 0 | 1 | 1 | 1 | 0 | 0.5 | 0.5 |  | 4 | 2015
| 4303 | GOME2 OClO validation | 0 | 0 | 0 | 3 | 2 | 0.25 | 5.25 | 6.96 | 36.54 | 18.27 | 0.5 |  |  |  |  | 2016 | 0 | 1 | 1 | 1 | 0 | 0.5 | 1 |  | 4.5 | 2016
| 4304 | GOME2 HCHO validation & QA | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 2.75 | 6.96 | 19.14 | 14.355 | 0.75 | QA |  |  |  | 2017 | 0 | 0.25 | 0.25 | 0.5 | 0 | 0.25 | 0.25 |  | 1.5 | 2017
|  |  | 0 | 1 | 1.5 | 0 | 1 | 0 | 3.5 | 6.96 | 24.36 | 12.18 | 0.5
| 4307 | GOME2 CHOCHO validation & QA | 0 | 0 | 0 | 0.5 | 1 | 0.25 | 1.75 | 6.96 | 12.18 | 9.135 | 0.75 | QA |  |  |  | tot | 0 | 3.25 | 3.25 | 3.5 | 0 | 1.75 | 1.75 |  | 13.5 | tot
|  |  | 0 | 0 | 0 | 3 | 3.5 | 0 | 6.5 | 6.96 | 45.24 | 22.62 | 0.5
| 4313 | IASI HNO3 validation | 0 | 0 | 0 | 3 | 3 | 0.25 | 6.25 | 6.96 | 43.5 | 21.75 | 0.5
| 4100 | Reprocessing validation | 0 | 4 | 0 | 0 | 7 | 0 | 11 | 6.96 | 76.56 | 57.42 | 0.75 | QA | TOT EUMETSAT
[15 empty] | 50% share | 75% share | all: |  | TOT (EUM and nat):
| Total |  | 15.9 | 26.8 | 21.6 | 32.85 | 33.4 | 2 | 132.55 |  | 922.548 | 514.344 |  |  | 355.134 | 159.21 | 514.344 |  | 922548
| Travel | [7 empty] | 8.5 |  | 17 | 15.46 | 0.5 | 29580 | 8.5 |  | ok avec site web |  | ok avec site web
|  | The SG convert one person month from the BIRA WP 1306 | [8 empty] | 939.548 | 529.804 |  |  | 522.844
(year 2013) as an increase of the BIRA travel budget. One pm is equivalent to
the increase from 17000€ to 23960€
| Travel (euros) |  | 4792 | 4792 | 4792 | 4792 | 4792 | 0 | 23960 |  |  |  | (tot at beg 2014)
|  | spent: | 2012: 3579.35; 2013: 6088.28; 2014: 1009 | 10676.63
|  |  | cost rep. | cost rep | estim 7/2014
|  |  | 3to11/2012 | 12/2012-11/2013 |  | 1,5 MM from WP 4302 (valid SO2) ?
1 MM from WP 4303 (valid OClO) – ou garder un peu pour 2eme partie 2014 pour après le VS??
3 MM from WP 4307 (valid CHOCHO) to 2015 or later
1.5 MM from WP 4313 (valid HNO3) to later (RR planned for end 2015)
asked to Seppo, in the entity report of 10/2014:
2014/10: Requests for work modifications / payment reallocations (if any):
According to the changes in the product development schedule and to NO2 validation needs, we would like to shift:
- 1 MM tropospheric NO2 development (WP 1202) from 2014 to 2015
- 1 MM total NO2 development (WP 1202) from 2014 to 2015
- The 2 MM total BrO development (WP 1301) of 2014 to validation of SO2 (for IASI) (WP 4302), 1 in 2015 and 1 in 2016.
- 1 MM tropospheric BrO development (WP 1311) from 2014 to 2015
- 1 MM OClO development (WP 1303) from 2014 to validation of NO2 (WP 4202) in 2014
- 1 MM CHOCHO development (WP 1306) from 2014 to 2015
- The 2 MM of valid BrO (WP 4301) of 2014 to 2015.
- The 1 MM of valid OClO (WP 4303) of 2014 to be moved to the validation of NO2 (WP 4202) in 2014.
Note on G11: Author: it was 2/1/0,7
Note on E18: Author: it was 2, nut asked in 10/2013 toreallocate 1 of 2 MM to travel!!! --> 6960euro to be spread on the next 3 years
Note on G19: Author: move 1,7MM to WP 1610 but how??? It was 2/1/0,7
Note on E29: Author: it was 2 in 2013 and 2 in 2014, 1 in 2015 and 1 in 2015
Note on C32: Author: I checked the CHOCHO plan from the Master Schedule: - PCR 30.06.2014 - ORR 30.09.2015
Note on F32: Author: from 2104 onward, it was: 0.5, 0.5, 0.5 and 0.25
Note on E33: Author: it was 3 and 2,5 in 2014 0 in 2015 and 0,5 in 2016,
Note on G33: Author: Seppo propose to close de validation in 2015 because the product should be ready at that point and we need validation only before, and the it's the QA!!
Note on F43: Author: sum of remboursement and flight for Helsinki mission Gaia